## Sheet1
|  | Project Name: | IMS Project
|  | Project Description: | Functional application to interact with a managed database
|  | Project Owner: | Claes Alfonso
Risk ID | Date registered | Risk area | Risk description | Probability |  |  | Risk Level |  | Project impact | Proximity / Length of impact | Response strategy
1 | 18.12.20 | covid-19 |  |  |  | x |  | x
2 | 4.01.2021 | Google Cloud Platform | Forgetting to close cloud SQL instance |  | x |  |  | x | 0% | Minimal project effect, however a big cost effect | Always close GCP instance after use, do not let it run overnight
3 | 4.01.2021 | Computer crashing | Loss of data due to computer crashing or damage |  | x |  |  | x | 100% | Long | push to github frequently
4 | 5.01.2021 | Merge conflicts within git | Git merge could create a merge conflict |  | x |  | x |  | 20% | Short | Minimise duplicate items
5 | 11.01.2021 | Application breaks | Application could break due to errors or other software issues |  |  | x |  | x | 100% | Medium | Break up larger functions into smaller pieces